AES Clean Energy PRC-028 Portfolio Compliance

Burns & McDonnell proposes to provide an integrated design, procurement, and onsite services offering to support AES Clean Energy in addressing PRC-028 requirements. This approach provides a single point of contact for project coordination and leverages AES Clean Energy’s standardized Tesla 4000A hardware platform to deliver a scalable, consistent solution across the portfolio.

Scope Summary

To address the scale and complexity of this program, Burns & McDonnell proposes a strategic EPIC (Engineer, Procure, Install, Commission) approach executed in two distinct phases per site. This structure provides cost certainty for engineering while managing the variables of construction through a budgetary framework that is refined after site verification. By maintaining the same project team from design through commissioning, we ensure that the specific site knowledge gained during verification is directly applied to the installation, minimizing rework and schedule delays.

Phase 1 (Engineering)

This phase is structured using unit pricing with a milestone-based payment structure, providing AES Clean Energy with immediate cost certainty on the design and material specification deliverables while preparing the specific scope required for physical implementation. By executing this phase first, we mitigate downstream risks by confirming rack locations, cable paths, and tie-in points before procuring major hardware or mobilizing construction crews.

Phase 2 (Procurement, Installation, and Commissioning)

Our team capitalizes on the continuity of involvement from inception, to site visit, through design to seamlessly provide a firm fixed price for execution based on the finalization of the Phase 1 design. Phase 2 encompasses the procurement of the site-specific Tesla 4000A equipment, mobilization of field teams, and the installation and commissioning of the DFR(s). Execution is planned and scheduled in alignment with the site-specific outage windows and operational constraints identified during Phase 1 and in collaboration with AES Clean Energy to meet their outage needs.

Phase 1 Overview - Engineering

Phase 1 covers the comprehensive engineering and design services required to retrofit existing sites with Tesla 4000A Disturbance Fault Recorder(s) (DFRs). The process begins with Design Scoping & Site Verification, where our team reviews existing record drawings to prepare pre-site visit verification markups and conducts physical site walk-downs to validate constructability, cable paths, and tie-in points.

Following verification, we will develop the detailed design drawings through a collaborative review process to ensure alignment with AES Clean Energy standards. This includes the submission of 60%, 90%, and Issued for Construction (IFC) design packages, with each stage allotted a 10-day review window for AES Clean Energy feedback. This structured approach ensures that the final Bill of Materials (BOM) and construction scope are fully validated prior to Phase 2 execution.

Design Scoping & Site Verification

Upon award, Burns & McDonnell will initiate a preliminary design process to prepare the specific scope of work to be verified during the site visit with AES. This effort focuses on validating existing conditions to support a final design that is constructible and accurate.

Pre-Site Visit Engineering & Scoping

Our team will review the existing site record drawings provided by AES to establish the basis for the design. We anticipate reviewing the following documents:

Single Line and Three Line Diagrams

AC/DC Schematics and Wiring Diagrams

Panel Elevations and Control Building Plan Views

Existing Cable Schedules

Based on this review, we will develop a Preliminary Design Scoping Package to serve as the agenda for the site walk-down. This package will include redline markups identifying:

Proposed placement of the new Tesla 4000A rack(s), wall-mount, or existing panel location

Targeted tie-in points for Analog Inputs (CTs/PTs) and Digital Inputs (Breaker Statuses)

Provisional cable routing paths through existing trays or conduits

Site Verification Walk-Down

Burns & McDonnell will mobilize to the site to lead a walk-down with AES personnel. Utilizing the Preliminary Design Scoping Package, we will verify the proposed design against actual field conditions. The primary objectives of this visit include:

Confirming the physical space availability in the Control House aligns with the proposed rack, wall-mount, or existing panel location

Establishing if existing cable trays within the control house are sufficient or if new conduit/tray is required

Visually verifying that spare breaker contacts are available at the control house termination points

Collaborating with site operations regarding preliminary outage constraints and schedule alignment

- Following the site visit, Burns & McDonnell will summarize the findings to confirm the final scope of work and identify any deviations from the preliminary markups. This summary will serve to finalize the execution plan prior to the commencement of detailed design.

Design Services

Burns & McDonnell will execute the detailed design to support PRC-028 compliance prior to mobilization. Our team will provide a sealed Issued for Construction (IFC) design package that includes the following deliverables:

Non-Drawing Deliverables

Design Basis Document (DBD)

Bill of Materials (BOM)

Method of Procedure (MOP)

Channel Assignments

Tesla 4000A Settings File(s)

QA/QC Checklist

PRC-028 Compliance Report

Construction Sequence of Events

Electrical Design Deliverables

Single Line Diagrams

Three Line Diagrams

AC/DC Schematics

Control Panel Elevations

Control Building Plan View

Drawing List

Wiring Diagrams

Cable Schedule

DC Calculations (as required)

Comm Block Diagrams

Electrical design deliverables are limited to updates to existing drawings impacted by the new Tesla 4000A installation. Creation of new drawings, including calculations, is limited to the specific rack or panel layouts required for the new DFR equipment; full re-creation of existing site drawing sets is not included.

Project Management

Burns & McDonnell’s project manager will provide general project administration, budgeting, invoicing, change management, and day-to-day management and coordination of the internal Burns & McDonnell engineering team. During Phase 1, the Project Manager will focus on facilitating site verification logistics and coordinating the timely submission of drawing packages to meet the 10-day review windows. Additionally, our team will develop and maintain a detailed project schedule that tracks key design milestones and aligns future construction activities with AES Clean Energy’s site-specific outage windows. Burns & McDonnell will coordinate and provide project updates during bi-weekly virtual meetings with AES Clean Energy. These updates will include an overview of project progress, schedule updates, action item logs, RFI logs, change logs, and invoicing updates.

Phase 2 Overview - Procurement, Installation, and Commissioning

Phase 2 encompasses the physical execution of the project, transitioning from the engineering definition in Phase 1 to on-site implementation. Upon finalization of the design and approval to proceed, Burns & McDonnell will initiate Procurement, leveraging the equipment packages prepared during Phase 1 to minimize lead times for the site-specific Tesla 4000A unit(s).

Following material delivery, we will mobilize qualified field teams to perform Site Work - Installation and Commissioning. All physical activities will be executed in accordance with the AES CE OPS EHSS Electrical Safety Program and the AES-approved Method of Procedure (MOP), ensuring work is coordinated with AES Clean Energy operations to align with site-specific outage windows. This phase concludes with the submission of the PRC-028 Compliance Report and final As-Built documentation.

Procurement

Burns & McDonnell will manage the procurement of major equipment and ancillary materials required for the site-specific Tesla 4000A solution. This scope includes vendor management, tracking manufacturing lead times, and coordination of shipping logistics to ensure all materials are available on-site prior to the scheduled outage window. By handling procurement directly, we ensure equipment specifications align with the design package and minimize the risk of construction delays. This supply scope includes:

Tesla 4000A DFR unit(s)

Ancillary hardware, including Racks/Panels, Test Switches, Terminal Blocks, and Cabling

Site Work - Installation

The Burns & McDonnell Integration Services team will deploy qualified electrical crews to perform the necessary physical installation activities within the substation control enclosure. Work will be executed in accordance with the AES CE OPS EHSS Electrical Safety Program and the AES-approved Method of Procedure (MOP), utilizing personnel qualified for work in energized environments to minimize outage requirements. Our team will handle the installation of new hardware and the termination and labeling of power, control, and communication cabling required to integrate the new DFR(s) into the existing SCADA system and AES network.

Install Tesla 4000A rack(s) or wall-mount panel(s) in the existing control house

Terminate one (1) standard set of cables per Tesla unit (Power, Analog Inputs, Digital Inputs, Comms, IRIG-B)

Install and terminate cabling from Metering CTs to DFR for harmonic capture (as required)

Site Work - Commissioning

Following installation, Burns & McDonnell will execute the commissioning activities outlined in the AES-approved Method of Procedure (MOP). This testing validates the performance of the Tesla 4000A DFR(s) and supports the facility's adherence to NERC PRC-028 standards. All testing results will be documented in the AES-provided QA/QC Checklist and the final PRC-028 Compliance Report. Commissioning activities will include:

Verifying physical wiring terminations at the DFR

Verifying DFR triggering, recording accuracy, and proper channel scaling

Coordinating with AES IT/OT to verify IP connectivity, remote access, and successful file retrieval

Confirming transmission of DFR health alarms (e.g., "Device Healthy," "Memory Full") to the local RTU/SCADA system

Validating IRIG-B synchronization and timestamp accuracy

Upon successful completion of testing, Burns & McDonnell will compile and submit the final documentation package, including the finalized Settings File(s), As-Built Drawings, and the completed PRC-028 Compliance Report.

Project Management

During Phase 2, the Burns & McDonnell Project Manager will transition focus to the active management of procurement, construction, and commissioning activities. This role involves coordinating the mobilization of field teams to align with the confirmed outage windows defined in Phase 1. The Project Manager will oversee logistics to ensure all procured equipment is staged on-site prior to crew arrival and will maintain open communication channels with AES Clean Energy site operations to track progress and manage critical path activities. Additionally, the Project Manager will provide high-level oversight to ensure all personnel maintain required qualifications and that the project execution aligns with the approved safety and quality plans.

Assumptions & Clarifications

Burns & McDonnell is committed to a flexible approach that meets the needs of this project. A thorough review of the project scope will be an important part of the kick-off meeting to confirm the scope of work overviewed in this proposal meets the needs of the project. To further define the scope as currently proposed, please review the following assumptions and clarifications:

- Pricing presented in this proposal is based upon the scope as outlined above and AES Clean Energy design specifications at the time of Approval to Proceed.

- It is assumed that all phases of this work will occur in 2026. Should any work be delayed to future years, a change order may be necessary to accommodate rate adjustments.

- Pricing is based on a continuous workflow where Phase 2 execution follows Phase 1 engineering with minimal delay (less than 14 days). Extended delays between phases may require a pricing adjustment to account for the additional project management and coordination efforts required to maintain project continuity during the lag.

- If site work is delayed during an outage or rescheduled after resource deployment due to circumstances beyond Burns & McDonnell's control, a change order may be required.

- To ensure safety and quality, on-site work is assumed to be performed during standard shifts of up to twelve (12) hours per day, Monday through Friday. While Burns & McDonnell can support continuous (24/7) or weekend operations if required by specific outage constraints, such requirements will be subject to a pricing adjustment.

- Current engineering drawings are assumed to be out-of-date. Any rework made necessary due to undocumented differences between drawings and site conditions will result in schedule and/or budget changes.

- CAD files of existing drawings will be provided by AES Clean Energy in AutoCAD format. Burns & McDonnell has not included design efforts for re-creation or as-built updates of site drawings not directly impacted by this effort.

- This proposal assumes that the AES Clean Energy provided CAD standards (B-2.1), blocks, and reference drawings are complete and functional. In the event of a conflict between the AES standards and the existing site layout, the existing site layout and format shall take precedence. Any significant effort required to modify provided standards or create new custom templates to match existing site formats is excluded.

- The design assumes the utilization of the standardized Tesla 4000A architecture for monitoring applications only. Modification of existing protective relay settings, control logic schemes, or tripping circuits beyond the necessary monitoring tie-ins is excluded.

- Final acceptance of the Design Basis Document and its capability to comply with PRC-028 will be determined and approved solely by AES Clean Energy.

- This proposal assumes that an existing IRIG-B time synchronization infrastructure is present, functional, and available to support the new DFR(s). Any required additions, modifications, troubleshooting, or correction of time distribution hardware are excluded from this scope and assumed by Others.

- DC calculations are limited to the incremental load addition of the new DFR equipment. This proposal assumes the existing AC/DC auxiliary systems have sufficient available capacity to support this addition. Full facility-wide AC/DC load studies or battery sizing calculations are excluded.

- Phase 2 pricing is provided as a budgetary estimate and will be converted to a Firm Fixed Price upon completion of the Phase 1 design, confirmation of material and freight costs, and finalization of outage duration and coordination requirements.

- Major equipment (Tesla DFR(s)/Control Panel(s)) will be shipped directly to the site address. It is assumed that AES Clean Energy personnel will receive and inspect the equipment upon delivery, and that all materials will be staged and readily available on-site at the time of mobilization. Special handling, off-site storage, or long-term warehousing fees are excluded.

- To perform the on-site testing and commissioning activities, Burns & McDonnell and its authorized subcontractors must have unimpeded and safe access to all necessary work areas and equipment.

- Any work required on energized systems/equipment is outside the scope of this proposal and, if requested, would be addressed via separate authorization.

- Final Relay Testing Report will be provided 30 days after completion of testing

- Configuration files provided to Burns & McDonnell for relay settings, the substation RTU, and the substation PC/PDC application are assumed to accurately represent the as-found configurations at the site at the time of commissioning. Discovery of configuration discrepancies may result in schedule delays, outage extensions, and additional costs.

- Burns & McDonnell’s pricing and schedule assume the development of one (1) Design Basis Document revision. Requests by Apex Clean Energy to materially modify the proposed solution approach may result in schedule and/or budget adjustments.

- Existing devices serving a disturbance monitoring equipment (DME) function are capable of being configured to meet applicable NOGRR-255 requirements without the need for firmware upgrades, licensing changes, device replacement, or supplemental hardware.

- Installation activities under this scope are limited to existing substation control enclosures, cabinets, and relay panels.

- Any switch configuration changes, firewall rules, port or service enablement, or other network or cybersecurity control changes required to support communications are excluded from this scope and are assumed by Others.

- Existing site Ethernet and communications infrastructure required to support configuration, data collection, and testing activities for applicable devices will remain available and operational for the duration of all on-site activities.

- Configuration updates to the existing substation RTU and substation PC hosting the Phasor Data Concentrator (PDC) application will be limited to functionality required to meet applicable NOGRR-255 requirements.

- Any new cabling installed under this scope will be routed through existing cable tray and/or conduit. No new cable tray or conduit installation, modifications, or fill calculations are included in this scope.

- This proposal assumes Apex Clean Energy will oversee the substation outage, including establishing required isolations and placing affected devices and associated wiring in a state that allows configuration, testing, and commissioning activities to be completed with no effect on other substation equipment.

- Burns & McDonnell and its authorized subcontractors must be able to review substation lockout/tagout (LOTO) and isolation plans and will be designated as tagging authorities to apply their own locks for the duration of on-site activities. If Apex Clean Energy, a contractor, or a third party requires modifications to isolation points or the LOTO plan, Burns & McDonnell and its authorized subcontractors will be included in the coordination prior to implementation of any such changes.

- During on-site activities, the substation will retain functional AC and DC power necessary to support configuration, testing, and commissioning. In addition, a minimum of two (2) dedicated 120 VAC, 20-Amp power circuits within one hundred (100) feet of the relays to be tested will be available to support relay testing activities.

- This proposal assumes on-site activities can be performed over three (3) consecutive working days, with workdays of up to twelve (12) hours per day, and that two relay technicians will be able to perform relay testing in parallel, sufficient to complete all planned configuration, testing, and commissioning activities.

- If the assumed on-site work duration, work pattern, or outage window cannot be accommodated, the outage duration required to complete the work may be extended, and additional costs may be incurred.

- Project schedule dates are based on the assumed Task Order issuance and authorization to proceed. Any delay in Task Order issuance or authorization to proceed will result in a corresponding day-for-day shift to the project schedule.

- This proposal assumes major equipment procurement will be completed by Apex Clean Energy and equipment will be readily available on site at the time of mobilization. Truck stock and cabling will be provided by Burns & McDonnell as part of this proposal.

- This proposal does not include any services for updates to engineering drawings where updates by others have been completed but not recorded to the official drawings.

- Existing inputs, signals, and data sources used to support disturbance monitoring and event recording are assumed to be present, functional, and in good working order. Any troubleshooting, repair, or correction required to restore functionality of these inputs, signals, or data sources is excluded from this scope and assumed by Apex Clean Energy/Others.

- Deliverables for the relay settings include modified setting files and compare reports to identify the changes made. Supporting documentation justifying the changes is not included in this estimate and can be provided at additional cost if required by Apex Clean Energy.

- All Test Procedures for testing of updated relays will be in accordance with the International Electrical Testing Association (NETA) Acceptance Testing Specifications. Should the client require alternative test procedures, these must be specified in writing and formally accepted by Burns & McDonnell.

Schedule

Burns & McDonnell is committed to a flexible approach that meets the needs of this project. Based on our current understanding of the project scope, we have assumed the following project schedule:

| MILESTONE | TASK OWNER |  | Dates |
| --- | --- | --- | --- |
|  | AES Clean Energy | BMcD |  |
| Approval to Proceed (ATP) | X |  | 3/11/26 |
| Kick-Off Meeting/Site Visit Coordination | X | X | 3/16/26 |
| Site Visit Conducted | X | X | 2/13/26 |
| All Design Inputs Provided | X |  | 2/13/26 |
| DBD Submitted |  | X | 2/20/26 |
| DBD Approval | X |  | 2/27/26 |
| IFA Package Submittal |  | X | 3/27/26 |
| IFA Package Comments Due by Apex Clean Energy | X |  | 4/10/26 |
| 100% Engineering Package IFC |  | X | 4/17/26 |
| Outage Pre-Coordination Meeting | X | X | 4/22/26* |
| Installations, Testing & Commissioning |  | X | 5/4/26* |
| Closeout – Punch List Review | X | X | 5/8/26* |
| Closeout – As Built Drawings |  | X | 7/3/26* |

*Note: Dates shown are preliminary. Actual dates will be finalized and agreed upon once the site outage dates are confirmed.

Compensation

Burns & McDonnell proposes completing the services on a lump-sum milestone payment schedule as outlined below. Pricing is valid for 30 days from the initial proposal submittal.

Pricing Breakdown

| PACKAGE | DESCRIPTION | TOTAL COST |
| --- | --- | --- |
| 1 | Phase 1 Services | $145,000 |
| 2 | Phase 2 Services (Budgetary) | $250,000 |
| Total |  | $395,000 |

Milestone Payments

The amounts specified below are fixed and constitute complete compensation for all services. No retention shall apply to payments by Apex Clean Energy to Burns & McDonnell for the Services.

| DESCRIPTION | MILESTONE % | MILESTONE PAYMENT |
| --- | --- | --- |
| Project Award / Notice to Proceed | 20% | $ |
| Approval of Design Basis Document | 20% | $ |
| Submittal of IFC Engineering Drawings | 25% | $ |
| Two (2) weeks prior to Field Team Deployment | 25% | $ |
| As-Built Drawing Submittal | 10% | $ |
|  | Total | $ |